## Slide 1: Project Management Discipline Scope
Solution Architecture
Version 0.2 – Joseph Alexander
1

## Slide 2: Version control
2
Version | Description | Author
0.1 | Initial draft | Joseph Alexander
0.2 | Updated after business inputs | Joseph Alexander
DRAFT

## Slide 3: Overview
3
  Background
  Enterprise has chosen MSP as the tool for project management related functions.
    MSP is currently used in several branches within the Enterprise (IT and construction)
    A scope definition is required and requires clarification of scope for what will be implemented is MSP.
    End-to-end process with clear scope differentiation has been requested.
  Purpose of this document
  This document defines the business functions carried out in the project management end-to-end process and which solution (ASAP or MSP) will be used to support the function.
  The definitions in this document will be used to inform the following;
    The scope for a business case to implement MSP across the Enterprise.
    Potential changes required to the processes or solution scope for ASAP.
    The more detailed requirements for the integration of ASAP to MSP.
  Approach
  The content of this document will be agreed in Consultation with the Enterprise IT.
  Scope change for ASAP will be managed through the ASAP program governance processes.
  Acronyms
  MSP – MS Projects
  ASAP – Accelerated SAP

## Slide 4: Project management discipline scope
4
Discipline | Description | ASAP Scope | Non-ASAP Scope
Structures ASAP – high level, organisational monitoring Non-ASAP - detail view, project control | Standard projects; that can be used as a template when creating a new project, used to standardise the basic project structures across the organisation. | X | 
 | Project Definition; Name of the individual project | X | 
 | Work Breakdown Structure Elements; objects in the system used to break up a project and provides a reporting structure | X | 
 | Network; network of project activities | X | 
 | Internal network activity; project activity performed by BCC internal staff/ Contractors |  | X
 | Planning for general cost; primary costs, labour, materials, expenses | X | 
 | Work order, Ownership is in SAP; (work orders will not be interfaced to MSP) | X | 
Scope | Definition of the project scope and storage of project documents (TRIM) |  | X
Time | Milestones (critical/high level reporting dates – start and end dates: linked to MSP start and end dates) | X | 
 | Project scheduling; setting out the project activities in time; by planning the activity duration and maintaining the Finish-Start relations between the activities |  | X
Cost/ Revenue | Overall Budgets; will be managed in SAP BPC and distributed to SAP PS/ PPM | X | 
 | Planned costs; Planned costs will be maintained in SAP PS. When using network costing the inputs would come out the of MSP project schedule. | X | 
 | Operational Forecast costs calculation and reporting (using an activity based structure) |  | X*
 | Actual costs; Actual costs are maintained in SAP, the SAP PS project will receive costs from SAP MM, CATS, and FICO. The actual costs will be interfaced to SAP PPM/BPC. | X | 
 | Sales revenue will be managed in SAP (using SD and AR) | X | 
 | Contingency planning (to be included in the planned cost) |  | X
Mgt of Change | Change request process to be managed outside of SAP (The Financial implications of the change would be updated in SAP PS) |  | X
 | The scheduling implications of the change would be updated in MSP |  | X
* Inclusion of forecasting in ASAP would require a change of scope from the ASAP Business Case

## Slide 5: Project management discipline scope
5
Discipline | Description | ASAP Scope | Non- ASAP Scope
Quality | Quality tasks will be integrated in the project schedule |  | X
Resources | Maintain resource data; maintaining details for resources will be done in SAP HR. | X | 
 | Capacity management | X | 
 | Resource allocation and Resource levelling for Divisions/Branches that manage their resources using work orders and Clicksoft will be managed in SAP | X | 
 | Resource allocation and Resource levelling for Divisions/Branches that do not manage their resources via work orders and Clicksoft will manage the resources via MSP. |  | X
Knowledge Mgt | Knowledge management will be done in TRIM. Some parts of the organisation will use network drives, mostly when working with large CAD drawings. |  | X
Communications | Communication plans will be stored in TRIM; Distributing communications will be done outside or SAP and MSP. Communication tasks can be included in the project schedule in MSP. |  | X
Risk and Issues | Risks and issues will be maintained in lists in MSP; If contingency planning is done on an individual risk level; a cost activity can be included in SAP PS to plan a contingency for the risks Activities can be scheduled that will consume the contingency when the risk becomes an issue, or actions taken to prevent the risk from becoming an issue |  | X
Sourcing and Contracting | Procurement of services (subcontractors) and goods will be done in SAP | X | 
Performance Mgt and Reporting | Status Reporting from MSP |  | X
 | Budget Reporting from SAP BI (using the PPM structures) | X | 
 | Operational Financial Reporting from SAP PS/ PPM | X | 
Governance and Assurance | Project governance and assurance will be maintained offline |  | X
Workplace health and safety | Incident recording, management and reporting Workplace risk assessment and management (excludes corporate risk) | X | 

## Slide 6
- Project Definition
- WBS Element
- Network Activity
- WBS Milestone
- Relationship
AIS
Cost Capture
AUC
SAP PS
Software
Hardware
Posting Object
Reporting Object
90%
Jan’14
IT
$ 300K
S-50 Lic
S 450k
Project Definition
Feb’14
IT
$ 200K
10%
H-1 EA
$ 50k
Feb’14
Phase 1
Task 1
Task 2
IT
Phase 2
Task 3
Task 4
Phase 3
Task 5
Phase 4
Task 6
Phase 5
Task 7
X
-
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
Project
Summary Task – Phase1
Task 1
Task 2
IT Summary Task
Summary Task – Phase2
Task 3
Task 4
Summary Task – Phase3
Task 5
Sum.Task – Phase 4
Task 6
Sum. Task – Phase 5
Task7
M.Task
M.Task
M.Task
MS Project
A
A
A
A
A
A
A
A
A
B
B
B
B
B
B
B
- Data Transferred from SAP to MSP(Project/Phase Milestone-Dates –Create/Change)
- Data Transferred from MSP to SAP(Detailed Task/Date/Duration/Relationship – Create/Change)
Note: Deletion will not be allowed in SAP and MS EPM. Deletion Indicator will be updated both ways.
B
SAP Object
Transfer
Indicator
SAP EPC
Budget
Cost Allocation
Procurement
Procurement & Timesheet at same level
Timesheet
Scenario 1 – Structure is the same in both Systems
A

## Slide 7
- Project Definition
- WBS Element
- Network Activity
- WBS Milestone
- Relationship
AIS
Cost Capture
AUC
SAP PS
Bikeway
Footpath
Posting Object
Reporting Object
90%
Jan’14
PMC
$ 300K
B-5 km
S 350k
Project Definition
Feb’14
PMC
$ 200K
10%
F-5 km
$ 150k
Feb’14
C1: Planning
Task 1
Task 2
PMC
C2: Design
Task 3
C3: Construction
Task 5
C4: Proj Mgmt.
Task 6
C5: Land Acq
Task 7
X
-
X
X
X
-
-
X
X
-
X
X
-
X
X
-
X
X
X
Project
Sum. Task -Phase1
Task 1
PMC Summary Task
Sum. Task – Phase2
Task 3
Task 4
Sum.Task – Phase3
Sum. Task – Phase4
Task 6
Sum. Task – Phase 5
Task 7
M.Task
M.Task
MS Project
A
A
A
A
B
B
B
B
B
B
B
- Data Transferred from SAP to MSP(Project/Phase Milestone-Dates –Create/Change)
- Data Transferred from MSP to SAP(Detailed Task/Date/Duration/Relationship – Create/Change)
Note: Deletion will not be allowed in SAP and MS EPM. Deletion Indicator will be updated both ways.
B
SAP Object
Transfer
Indicator
SAP EPC
Budget
Cost Allocation
Procurement
Procurement & Timesheet at same level
Timesheet
Scenario 2 – Detailed Task in MSP mapped to Cost Breakdown Structure
Assignation Type
C1
C1
C2
C4
C3
C4
C5
Assignation Type | Cost Breakdown Structure
C1 | Planning
C2 | Design
C3 | Construction
C4 | Project Management
C5 | Land Acquisition
C6 | Others
Project Schedule based on PMP
Project Structure based on Cost Breakdown Structure
Task 4
M.Task
A
Task 2
Task 5
C6: Others

## Slide 8
Scenario1:
Budget: Project Budget will be managed in SAP
Cost Management:
Cost Allocation related to Gen. Overhead, Corporate Overhead, Local Overhead, Activity Allocation, Timesheet and Procurement will be managed in SAP.
Standard rates will be managed in SAP
Resource Management: Resources to be set up manually in MSP and assignation to task will be performed in MS Project.
Schedules: Task schedules will be managed in MS Project with start/End Dates and dependencies.
Reporting:
Task Schedule Report: Gantt Chart from MS Project
Operational Project Reports: Plan Vs. Actual from SAP PS
Strategic Project Report: Budget Vs. Actual from BI.
Advantages:
Structure in SAP and MS Project are the same. Hence it is easy to manage and analyse.
Allows to cost labour delays.
Allows to report cost based on phases and tasks.
SAP Project Structure aligns to PMP Methodology.
Disadvantages:
Whole project will be exported and the respective branches have to work on their respective areas.
Scenario2:
Budget: Project Budget will be managed in SAP
Cost Management:
Cost Allocation related to Gen. Overhead, Corporate Overhead, Local Overhead, Activity Allocation, Timesheet and Procurement will be managed in SAP.
Standard rates will be managed in SAP
Resource Management: Resources to be set up manually in MSP and assignation to task will be performed in MS Project.
Schedules: Task schedules will be managed in MS Project with start/End Dates and dependencies.
Reporting:
Task Schedule Report: Gantt Chart from MS Project
Operational Project Reports: Plan Vs. Actual from SAP PS
Strategic Project Report: Budget Vs. Actual from BI.
Advantages:
Allows to report cost based on tasks.
Disadvantages:
Structure in SAP and MS Project are not the same. Hence it is not easy to manage and analyse.
Since the structure in both the systems are not the same, complex interface is required.
Does not allow to report cost based on phases.
SAP Project Structure is based on cost breakdown structure and does not align with the PMP Methodology.
Whole project will be exported and the respective branches have to work on their respective areas.