## Innovators & Early Adopters
Table 2-3: Recommended planning method for different types of planning, industry sector, delivery approach (managing or delivering projects) and Project Management Adoption Levels (Innovators, Early Adopters and Early Majority).
Innovators, Early Adopters & Early Majority (With higher project management maturity level) | Type of Planning | Public Sector (Councils, Transport, Department of Infrastructure, Regional Development Authorities, Water, Gas, Electricity, etc.) | Construction and Mining (Road, Rail, Plant, offshore Oil Rig, Hydro-electric, Power Station, tunnels, Airports, Home & Buildings, etc.) | Utilities –Telecom, Gas, Electricity and Water (Infrastructure Projects) | Other Turnkey Projects (Engineering, Design, Procurement and Erection, Commissioning Projects – Sewer, Waste Management Systems, Windfarms, Aeroplane Assembly, Ship Building, Heavy Machinery –Defence Equipment, Turbines and Pumps, etc.) | Professional Services (Information Technology (IT), IT enabled service, Legal, Property Management, Audit Firms, Media – Advertising, Event Management, etc.) | Chemical and Pharmaceutical (Paint R&D, Pharma R&D, Food & Drug Administrations, Therapeutic Goods Administrations, etc.)
Managing Projects (Mostly outsourced with minimum direct involvement in the project delivery. Volume of procurement contracts, number of persons being managed are less) | Estimate (P50, P90 Estimates) | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level
| Planning (Baseline Versions or Approved Planned Budget) | ECP (Quantity and Value) at WBSE Level | ECP (Quantity and Value) at WBSE Level | ECP (Quantity and Value) at WBSE Level | ECP (Quantity and Value) at WBSE Level | ECP (Quantity and Value) at WBSE Level | ECP (Quantity and Value) at WBSE Level
| Forecast (Estimate to complete (ETC) = Remaining cost + Approved and unapproved Variation’s cost (Internal and External)) | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value) at WBSE Level. Approved Internal and External variation claims should update ECP (Quantity and Value)*
| Variations (Approved and Unapproved Variation – both internal and external scope variations) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management at WBSE Level – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value)
| Forecast (Estimate at Completion (EAC) = Actual cost + Remaining cost + Approved and unapproved Variation’s Cost (Internal and External)) | Computed value in reports (Quantity and Value) at WBSE Level | Computed value in reports (Quantity and Value) at WBSE Level | Computed value in reports (Quantity and Value) at WBSE Level | Computed value in reports (Quantity and Value) at WBSE Level | Computed value in reports (Quantity and Value) at WBSE Level | Computed value in reports (Quantity and Value) at WBSE Level
Delivering Projects (Mostly delivered in house with higher direct involvement in the project delivery – Main contractors or sub-contractors. Volume of procurement contracts, number of persons being managed are high) | Estimate (P50, P90 Estimates) | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level | ECP (Quantity and Value) at project level
| Planning (Baseline Versions or Approved Planned Budget) | Network Costing (Quantity, Value and Date) at network activity level. | Network Costing (Quantity, Value and Date) | Network Costing (Quantity, Value and Date) | Network Costing (Quantity, Value and Date) | Network Costing (Quantity, Value and Date) | Network Costing (Quantity, Value and Date)
| Forecast (Estimate to complete (ETC) = Remaining cost + Approved and unapproved Variation’s cost (Internal and External)) | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)* | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)* | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)* | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)* | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)* | Remaining Work (Quantity, Value and date) of Network Activities, using Forecast Workbench. Approved Internal and External variation claims should create new variation network (Quantity, Value and Date)*
| Variations (Approved and Unapproved Variation - both internal and external scope variations) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date) | Claim Management – Approved Internal and External variation claims should create variation network (Quantity, Value and Date)*. Unapproved variation claims does not create new network (Quantity, Value and Date)
| Forecast (Estimate at Completion (EAC) = Actual cost + Remaining cost + Approved and unapproved Variation’s Cost (Internal and External)) | Computed value in reports (Quantity, Value and Date) | Computed value in reports (Quantity, Value and Date) | Computed value in reports (Quantity, Value and Date) | Computed value in reports (Quantity, Value and Date) | Computed value in reports (Quantity, Value and Date) | Computed value in reports (Quantity, Value and Date)
*Enhancement required.
Note: Recommended methods of estimate, planning, forecast and variation are interrelated and goes hand in hand with other types of planning, so that comparison of estimate, planning/planned budget and forecast can be achieved.
Definitions:
· Estimate to complete (ETC) is a forecast of how much more money will need to be spent to complete the project.
· Estimate at completion (EAC) is the forecasted cost to deliver the whole project, as the project progresses.

## Late Majority and Slow Adopters
Table 2-4: Recommended planning method for different types of planning, industry sector, delivery approach (managing or delivering projects) and Project Management Adoption Levels (Late Majority and Slow adopters).
Late Majority and slow adopters (With lower project management maturity level) | Type of Planning | Public Sector (Councils, Transport, Department of Infrastructure, Regional Development Authorities, Water, Gas, Electricity, etc.) | Construction and Mining (Road, Rail, Plant, offshore Oil Rig, Hydro-electric, Power Station, tunnels, Airports, Home & Buildings, etc.) | Utilities –Telecom, Gas, Electricity and Water (Infrastructure Projects) | Other Turnkey Projects (Engineering, Design, Procurement and Erection, Commissioning Projects – Sewer, Waste Management Systems, Windfarms, Aeroplane Assembly, Ship Building, Heavy Machinery –Defence Equipment, Turbines and Pumps, etc.) | Professional Services (Information Technology (IT), IT enabled service, Legal, Property Management, Audit Firms, Media – Advertising, Event Management, etc.) | Chemical and Pharmaceutical (Paint R&D, Pharma R&D, Food & Drug Administrations, Therapeutic Goods Administrations, etc.)
Managing Projects (Mostly outsourced with minimum direct involvement in the project delivery. Volume of procurement contracts, number of persons being managed are less) | Estimate (P50, P90 Estimates) | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers).
| Planning (Baseline Versions or Approved Planned Budget) | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers).
| Forecast (Estimate to complete (ETC) = Remaining cost + Approved and unapproved Variation’s cost (Internal and External)) | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | WBSE Cost Planning using Cost Element (CE) (Value); Quantity planning using SKF (Using standard functionality but both are not interconnected, giving flexibility for Project Managers). Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity
| Variations (Approved and Unapproved Variation – both internal and external scope variations) | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity | Claim Management – Approved Internal and External variation claims to update WBSE CE value and WBSE SKF quantity
| Forecast (Estimate at Completion (EAC) = Actual cost + Remaining cost + Approved and unapproved Variation’s Cost (Internal and External)) | Computed value in reports | Computed value in reports | Computed value in reports | Computed value in reports | Computed value in reports | Computed value in reports
Delivering Projects (Mostly delivered in house with higher direct involvement in the project delivery – Main contractors or sub-contractors. Volume of procurement contracts, number of persons being managed are high) | Estimate (P50, P90 Estimates) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value)
| Planning (Baseline Versions or Approved Planned Budget) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value) | ECP (Quantity and Value)
| Forecast (Estimate to complete (ETC) = Remaining cost + Approved and unapproved Variation’s cost (Internal and External)) | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)* | ECP (Quantity and Value). Approved Internal and External variation claims should update ECP (Quantity and Value)*
| Variations (Approved and Unapproved Variation - both internal and external scope variations) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value) | Claim Management – Approved Internal and External variation claims should update ECP (Quantity and Value)*. Unapproved variation claims does not update ECP (Quantity and Value)
| Forecast (Estimate at Completion (EAC) = Actual cost + Remaining cost + Approved and unapproved Variation’s Cost (Internal and External)) | Computed value in reports (Quantity and Value) | Computed value in reports (Quantity and Value) | Computed value in reports (Quantity and Value) | Computed value in reports (Quantity and Value) | Computed value in reports (Quantity and Value) | Computed value in reports (Quantity and Value)
*Enhancement required.
Note: Recommended methods of estimate, planning, forecast and variation are interrelated and goes hand in hand with other types of planning, so that comparison of estimate, planning/planned budget and forecast can be achieved.
Definitions:
· Estimate to complete (ETC) is a forecast of how much more money will need to be spent to complete the project.
· Estimate at completion (EAC) is the forecasted cost to deliver the whole project, as the project progresses.